## Sheet1
TASKS | Start Date | End Date | Remarks
Implement the same logic in kea report/dashboard that for consecutive call in the same week, call will count as one call-difficult to implement this. We can give information where such calls have happened. – can we give alert to user, when the doctor is already visited in the same week? | 2021-12-23 | 2021-12-23
System only calculate face to face call and video call – What other call types are the users entering now? We can implement that only F2F and video call should be counted. Wellesta leader give instruction that only F2F and Video will be counted as call | 2021-12-23 | 2021-12-23
User cant do DCR for back date activity – We can implement locking feature. If 3 days is set for locking period then after 3 days delay user will be locked out and will not be enter till unlocking is done by admin. This way there will be option to enter for old data. | 2021-12-21 | 2021-12-22
Mandatory on for GPS in Kea Apps – we can do this. Without this on reporting will not be allowed | 2021-12-20 | 2021-12-20
Voice assistance feature – is Bahasa getting recognized? It might not be 100% accurate but is it at least 80%? User can always correct the mistakes manually – I have tried the latest apk from ramesh, using Bahasa still no working | 2021-12-20 | 2021-12-20 | Need to check