## Sheet1
Module | DESCRIPTION | UI Status | API Integration (services) | End Date | REMARKS
Login Authentication | Fetching from live server | DONE | DONE |  | Functionality implemented only for Login authentication.
Home Screen | Greeting message will be displayed at the top along with notifications. | DONE | In Progress
| call plans count will be displayed. | DONE | In Progress | 22-10-2021 (EOD)
| DCR View, Missed Doctors, call plan and Effort KPI. By clciking on DCR View we are able to select the date. | DONE | In Progress | 25-10-2021(EOD) | Only DCR View functionality is done
DCR Main Screen | Selecting respective activity and by clicking on submit it will be redirect to Field Activity screen | DONE | In Progress | 27-10-2021(EOD)
| Add doctor call,Add unlisted doctor call, Add chemist call, Add stockiest Call options | DONE | In Progress | 27-10-2021(EOD)
DCR-Doctor Screen | Clicking on Add doctor call redirects to Doctor List screen where market area can be selected and the call plan. Search tab with list of doctors and its functionality will be displayed. By clciking on mail icon mail popup will appear. By clciking on Whatsapp icon Whatsapp popup will appear. By clciking on phone icon on last redirects to doctor call screen with options implemented and by cliking on next it will redirect to feedback screen with signature prompt (optional). | DONE | DONE | 2021-09-28 | Will be completed on 28-Sep-2021
DCR-Unlisted Screen | Clicking on Add unlisted doctor call redirects to Unlisted Doctor call screen along with the options displayed. we are able to select brand, sampling and Pob details here. Submit button checks whether the fields are filled or left blank with the prompt message. | DONE
DCR-Chemist Screen | Clicking on Add chemist call redirects to chemist list screen. Here by selecting on market area doctors list with search box will be displayed | DONE
DCR-Stockist Screen | Clicking on Add stockiest call redirects to stockiest list screen.Here by selecting on market area doctors list with search box will be displayed | DONE
Profile Screen | EMP code and last scync date | DONE | In Progress
| Logout button | DONE | DONE
| Syncronize and E-detailing button | DONE | In Progress
| Some fake buttons which can be changed in feature | DONE
Splash Screen |  | DONE
Intro Screen |  | In Progress
Loading Screen |  | DONE
My Leaves screen |  | In Progress |  | 2021-10-01
E Detailing screen |  | In Progress |  | 2021-10-01
Signature Screen |  | DONE
Permissions | Added all required permissions | DONE
Phone Call | calling is implemented, by clicking on doctor number able to do phone calls | DONE | DONE
Master Data Sync |  | DONE | DONE
Whatsapp |  | DONE | In Progress
Email |  | DONE | In Progress
Virtual Meeting |  | DONE | In Progress | 2021-09-29
Demo Changes Which happened on 24-Sep-2021 |  | DONE |  | 2021-09-28 | Refer Demo Feedback-24-Sep-2021 Sheet
Demo Changes Which happened on 28-Sep-2021 given by Madhu |  | DONE |  | 2021-09-29
Home Screen buttons DCR View, Missed Doctors, Effort KPI, Dr visit and Dr latest visit Screen options implemented | Date selection for DCR and Missed doctors popup implemented. Year selection for Effort Kpi to view data is implemented. Name,Month, Year selection for Dr visit and Dr latest Visit is implemented. | DONE
Notification Screen | Notification count will be displayed on new notifications. Able to click to view the notifications as a popup box | DONE

## Demo Feedback-24-Sep-2021
REACT APP DESIGN CHANGES
Changes | Status | End Date
Replace Emp Code with Emp Name | DONE
Color change to #ff5900 | DONE
Signature screen Deny button | DONE
Display Username along with Greetings in homescreen | DONE
Brand detailing, Sampling and POB Details dropdown listing | DONE
add on select. Remove Add button and list on selecting
Fencing doctor option | DONE
Use icons instead of text buttons in all place | In Progress | 2021-09-28
Icons on DCR screen | In Progress | 2021-09-28